## Sheet1
Test Summary Report
Report Date (dd-mm-yy): |  | 2026-02-17 |  |  |  |  | Version: | 1
Test Information
Project Name: |  | PaiNamNaeWebApp |  |  | Project ID: Product Backlog Item #11
Start Date (dd-mm-yy): |  | 2026-02-17 |  |  | End Date:18/02/2026
System/Module Name: |  | My Incident System
Test Specification Version: |  | As a driver, I want to report incidents to the admin and get the update on the filed case.
Testers: |  | secg3_1
Tester's comments:
Test Summary
No. of Test Cases in Test Specification Document: | [8 empty] | Case(s)
Test Type | [5 empty] | UAT | API
Planned: 4 |  |  |  | No. of Test Cases |  |  |  |  | Case(s)
Actual: 4 | [8 empty] | Case(s)
Passed: 2 | [8 empty] | Case(s)
Failed: 2 | [8 empty] | Case(s)
Total = 4 | [8 empty] | Case(s)
UAT Test Case
TCID |  | Module | Scenario | Expected Result |  | Actual Result |  | Status
Inc01 |  | Incident | คนขับต้องการสร้างรายงาน | ระบบสามารถสร้างการรายงานและผลลัพธ์ออกมาเป็น 200 |  | ผลลัพธ์ขึ้นเป็น 400 จึงไม่สามารถสร้างการรายงาน |  | Failed
Inc02 |  | Incident | คนขับส่งผลการรายงาน | คนขับสามารถดูหน้าจอผลลัพธ์การรายงาน |  | ผลลัพธ์ขึ้นเป็น 400 จึงไม่สามารถดูผลการรายงาน |  | Failed
Auth01 |  | Authentication | คนขับกรอกข้อมูลเพื่อสู่ระบบ | คนขับสามารถกรอกข้อมูลเข้าสู่ระบบได้ |  | ผลลัพธ์ขึ้นเป็น 200 คนขับสามารถกรอกเข้าสู่ระบบการใช้งานได้ |  | Pass
Auth02 |  | Authentication | คนขับเข้าสู่ระบบ | คนขับสามารถเข้าสู่ระบบได้ |  | ผลลัพธ์ขึ้นเป็น 200 คนขับสามารถเข้าสู่ระบบการใช้งานได้ |  | Pass
API Test
API ID | Endpoint | Method | Scenario | Expected Status |  | Actual Status | Response Time |  | Result
API-01 | /api/auth/login | POST | Login as driver | 200 |  | 200 | Pass |  | Pass
API-02 | /api/incidents | POST | Create incident | 200 |  | 400 | Fail |  | Fail
API-03 | /api/incidents/me | GET | View own incidents | 200 |  | 401 | Fail
Meaning
Defect Summary | [9 empty] | Severity Level | Impact | Description
No. of Defect Found: 2 | [9 empty] | 1 | Low | UI and presentation issues
|  |  |  | Severity Levels | [5 empty] | 2 | Medium | A feature is malfunction.
Low (1) |  |  |  | 0 | [5 empty] | 3 | High | Unexpected behaviour/results, software crash, data corruption
Medium (2) |  |  |  | 1 | [5 empty] | 4 | Critical | The function/software can not be run.
High (3) |  |  |  | 1
Critical (4) |  |  |  | 0
Note:
Effort Summary
Designing the Test: |  | 1 Person-hours | [5 empty] | Person-hours |  | Meaning
Test Setup: |  | 2 Person-hours | [5 empty] | Person-hours |  | Priority Level | Impact | Description
Test Execution: |  | 3 Person-hours | [5 empty] | Person-hours |  | 1 | Low | Minor issue or cosmetic defect that does not affect functionality. Can be fixed later or in next release.
Test Analysis and Report: |  | 7 Person-hours | [5 empty] | Person-hours |  | 2 | Medium | The defect affects a non-critical function or causes inconvenience, but there is a workaround available. Should be fixed soon.
Total Test Efforts: |  | 13 Person-hours | [5 empty] | Person-hours |  | 3 | High | The defect impacts core functionality and affects major parts of the system. Needs prompt attention before release.
Average Time Spend: |  | 7.5 Hours | [5 empty] | Hours/defect |  | 4 | Critical | The defect causes system failure, crash, or prevents further testing. Must be fixed immediately.