## Sheet1
Test Summary Report
Report Date (dd-mm-yy): |  | 18/02/2026 |  |  |  |  | Version:
Test Information
Project Name: |  | PaiNamNae |  |  | Project ID: Product Backlog
Start Date (dd-mm-yy): |  | 17/02/2026 |  |  | End Date: 18/02/2026
System/Module Name: |  | Report Incident
Test Specification Version: |  | As a passenger, I want to report the driver behavior to the admin and get the update on the filed case.
Testers: |  | sec3_1
สุจิรา พลอาษา
Tester's comments:
Test Summary
No. of Test Cases in Test Specification Document: | [8 empty] | Case(s)
Test Type | [5 empty] | UAT | API
Planned: |  |  |  | No. of Test Cases |  |  |  |  | Case(s)
Actual: | [8 empty] | Case(s)
Passed: | [8 empty] | Case(s)
Failed: | [8 empty] | Case(s)
Total = | [8 empty] | Case(s)
UAT Test Case
TCID |  | Module | Scenario | Expected Result |  | Actual Result |  | Status
TC01 |  | Report Incident | บันทึกรายงานเหตุการณ์สำเร็จ | Pass |  | Fail |  | Fail
TC02 |  | Report Incident | ตรวจสอบการบังคับกรอกข้อมูล | Pass |  | Pass |  | Pass
TC03 |  | Report Incident | ตรวจสอบการบังคับกรอกข้อมูล | Pass |  | Fail |  | Fail
TC04 |  | Report Incident | ตรวจสอบการบังคับกรอกข้อมูล | Pass |  | Pass |  | Pass
TC05 |  | Report Incident | ตรวจสอบรูปแบบ URL ของไฟล์แนบ | Pass |  | Pass |  | Pass
TC06 |  | Report Incident | ตรวจสอบขีดจำกัดจำนวนตัวอักษร | Pass |  | Pass |  | Pass
TC07 |  | Report Incident | ตรวจสอบขีดจำกัดจำนวนตัวอักษร | Pass |  | Fail |  | Fail
API Test
API ID | Endpoint | Method | Scenario | Expected Status |  | Actual Status | Response Time |  | Result
API01 | api/v1/incidents | POST | Report incident | 200 |  | 200 | Pass |  | Pass
Defect Summary
No. of Defect Found:
Severity Levels
Low (1)
Medium (2)
High (3)
Critical (4)
Note:
Effort Summary
Designing the Test: | [7 empty] | Person-hours
Test Setup: | [7 empty] | Person-hours
Test Execution: | [7 empty] | Person-hours
Test Analysis and Report: | [7 empty] | Person-hours
Total Test Efforts: | [7 empty] | Person-hours |  | Meaning
Average Time Spend: | [7 empty] | Hours/defect |  | Severity Level | Impact | Description
[10 empty] | 1 | Low | UI and presentation issues
| ใช้ AI ในการดูผลลัพธ์ที่ไม่รัน และมีส่วนช่วยในการทำ test case แต่ในการคิดtest case นักศึกษาเป็นคนทำเอง | [8 empty] | 2 | Medium | A feature is malfunction.
[10 empty] | 3 | High | Unexpected behaviour/results, software crash, data corruption
[10 empty] | 4 | Critical | The function/software can not be run.
Meaning
[10 empty] | Priority Level | Impact | Description
[10 empty] | 1 | Low | Minor issue or cosmetic defect that does not affect functionality. Can be fixed later or in next release.
[10 empty] | 2 | Medium | The defect affects a non-critical function or causes inconvenience, but there is a workaround available. Should be fixed soon.
[10 empty] | 3 | High | The defect impacts core functionality and affects major parts of the system. Needs prompt attention before release.
[10 empty] | 4 | Critical | The defect causes system failure, crash, or prevents further testing. Must be fixed immediately.