## Sheet1
Test Summary Report
Report Date (dd-mm-yy): |  | 2026-02-18 |  |  |  |  | Version: | 1
Test Information
Project Name: |  | sprint#1 |  |  | Project ID:sprint-1
Start Date (dd-mm-yy): |  | 2026-02-15 |  |  | End Date:18/02/2026
System/Module Name: |  | Admin Incident Update Module
Test Specification Version: |  | v1.0
Testers: |  | apiwich nararam
Tester's comments:
Test Summary
No. of Test Cases in Test Specification Document: | [8 empty] | Case(s)
Test Type | [5 empty] | UAT | API
Planned: |  |  |  | No. of Test Cases |  | 3 | 3 |  | Case(s)
Actual: | [5 empty] | 3 | 3 |  | Case(s)
Passed: | [5 empty] | 3 | 3 |  | Case(s)
Failed: | [5 empty] | 0 | 0 |  | Case(s)
Total = | [5 empty] | 6 | 6 |  | Case(s)
UAT Test Case
TCID |  | Module | Scenario | Expected Result |  | Actual Result |  | Status
UAT-INC-001 |  | Incident Management | Admin updates incident status | Status updated successfully and displayed to user |  | Status updated successfully and displayed to user |  | Pass
UAT-INC-002 |  | Incident Management | User views updated incident status | Latest status is displayed |  | Latest status is displayed |  | Pass
UAT-INC-003 |  | Incident Management | System sends notification after status update | Notification sent to user |  | Notification sent to user |  | Pass
API Test
API ID | Endpoint | Method | Scenario | Expected Status |  | Actual Status | Response Time |  | Result
API-INC-001 | /api/incidents/{id}/status | PUT | Update incident status with valid admin token | 200 ok |  | 200 ok | 60 ms |  | Pass
API-INC-002 | /api/incidents/{id} | GET | Retrieve updated incident | 200ok with updated status |  | 200 ok with updated status | 45 ms |  | Pass
API-INC-003 | /api/notifications | GET | Check notification after update | Notification record returned |  | Notification record returned | 30 ms |  | Pass
Meaning
Defect Summary | [9 empty] | Severity Level | Impact | Description
No. of Defect Found: |  |  |  | 0 | [5 empty] | 1 | Low | UI and presentation issues
|  |  |  | Severity Levels | [5 empty] | 2 | Medium | A feature is malfunction.
Low (1) |  |  |  | 0 | [5 empty] | 3 | High | Unexpected behaviour/results, software crash, data corruption
Medium (2) |  |  |  | 0 | [5 empty] | 4 | Critical | The function/software can not be run.
High (3) |  |  |  | 0
Critical (4) |  |  |  | 0
Note:
Effort Summary
Designing the Test: |  | 2 | [5 empty] | Person-hours |  | Meaning
Test Setup: |  | 1 | [5 empty] | Person-hours |  | Priority Level | Impact | Description
Test Execution: |  | 1 | [5 empty] | Person-hours |  | 1 | Low | Minor issue or cosmetic defect that does not affect functionality. Can be fixed later or in next release.
Test Analysis and Report: |  | 2 | [5 empty] | Person-hours |  | 2 | Medium | The defect affects a non-critical function or causes inconvenience, but there is a workaround available. Should be fixed soon.
Total Test Efforts: |  | 6 | [5 empty] | Person-hours |  | 3 | High | The defect impacts core functionality and affects major parts of the system. Needs prompt attention before release.
Average Time Spend: |  | 0 | [5 empty] | Hours/defect |  | 4 | Critical | The defect causes system failure, crash, or prevents further testing. Must be fixed immediately.
AI Usage Declaration เอกสารและสคริปต์ทดสอบบางส่วนในงานนี้ได้รับการช่วยเหลือจากเครื่องมือปัญญาประดิษฐ์ (AI) เพื่อช่วยในการ ตรวจสอบความถูกต้องของภาษา ปรับปรุงรูปแบบการเขียนรายงาน ให้คำแนะนำเกี่ยวกับโครงสร้าง Test Case และ Robot Framework ผู้จัดทำได้ทำการตรวจสอบ แก้ไข และยืนยันความถูกต้องของเนื้อหาทั้งหมดก่อนนำมาใช้งานจริง