## Sheet1
Test Summary Report
Report Date (dd-mm-yy): |  | 17/02/2026 |  |  |  |  | Version: | 1
Test Information
Project Name: |  | Sprint1-Pai Nam Nae |  |  | Project ID: |  | Sprint-1
Start Date (dd-mm-yy): |  | 17/02/2026 |  |  | End Date: |  | 17/02/2026
System/Module Name: |  | Account Deletion
Test Specification Version: |  | v1.0
Testers: |  | 1.นายพริษฐ์ ธรรมสอน
Tester's comments:
Test Summary
No. of Test Cases in Test Specification Document: | [8 empty] | Case(s)
Test Type | [5 empty] | UAT | API
Planned: |  |  |  | No. of Test Cases |  | 3 | 1 |  | Case(s)
Actual: | [5 empty] | 3 | 1 |  | Case(s)
Passed: | [5 empty] | 3 | 1 |  | Case(s)
Failed: | [5 empty] | 0 | 0 |  | Case(s)
Total = | [5 empty] | 9 | 3 |  | Case(s)
UAT Test Case
TCID |  | Module | Scenario | Expected Result |  | Actual Result |  | Status
UAT-001 |  | Account Deletion | Confirm Deletion | Account deleted successfully |  | Account deleted successfully |  | Pass
UAT-002 |  | Account Deletion | Cancel Deletion | Account is not deleted |  | Account is not deleted |  | Pass
UAT-003 |  | Account Deletion | Login After Deletion | Unable to log in |  | Unable to log in |  | Pass
API Test
API ID | Endpoint | Method | Scenario | Expected Status |  | Actual Status | Response Time |  | Result
API-001 | /api/users/me | DELETE | Delete account with valid token | 200 OK |  | 200 OK | 53 ms |  | Pass
Defect Summary | [9 empty] | Meaning
No. of Defect Found: |  |  |  | 0 | [5 empty] | Severity Level | Impact | Description
|  |  |  | Severity Levels | [5 empty] | 1 | Low | UI and presentation issues
Low (1) |  |  |  | 0 | [5 empty] | 2 | Medium | A feature is malfunction.
Medium (2) |  |  |  | 0 | [5 empty] | 3 | High | Unexpected behaviour/results, software crash, data corruption
High (3) |  |  |  | 0 | [5 empty] | 4 | Critical | The function/software can not be run.
Critical (4) |  |  |  | 0
Note:
Effort Summary
Designing the Test: |  | 2 | [5 empty] | Person-hours
Test Setup: |  | 1 | [5 empty] | Person-hours |  | Meaning
Test Execution: |  | 1 | [5 empty] | Person-hours |  | Priority Level | Impact | Description
Test Analysis and Report: |  | 1 | [5 empty] | Person-hours |  | 1 | Low | Minor issue or cosmetic defect that does not affect functionality. Can be fixed later or in next release.
Total Test Efforts: |  | 5 | [5 empty] | Person-hours |  | 2 | Medium | The defect affects a non-critical function or causes inconvenience, but there is a workaround available. Should be fixed soon.
Average Time Spend: |  | 0 | [5 empty] | Hours/defect |  | 3 | High | The defect impacts core functionality and affects major parts of the system. Needs prompt attention before release.
[10 empty] | 4 | Critical | The defect causes system failure, crash, or prevents further testing. Must be fixed immediately.
AI Declare (ChatGPT)
วัตถุประสงค์ในการใช้งาน
เพื่อช่วยในการอธิบายแนวคิดและทฤษฎีที่เกี่ยวข้องตรวจสอบโครงสร้างประโยคและความถูกต้องของภาษา
ขอบเขตการใช้งาน
การออกแบบระบบ การทดสอบ การวิเคราะห์ข้อมูล และการสรุปผลทั้งหมดเป็นผลงานของผู้จัดทำเอง